## Sprint 1
e | Hours(1st week) | Status | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19
Shahzeb | 7 hours 25 mins | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30min |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team 45min | Read through and looked at emails that we were sent to better understand the licensing issue taking place. Met with team in class, we sent emails to client to get a demo video of the application, and sent an email to the previous app team to understand what was going on with the licensing 2hours | Looked at demo video that client sent 20 mins | Created User story map, and organized user stories by category, then by priority 2 hours
Wilson | 10 hours 5 mins | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30min |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team 45min | Created basic user stories, discussed submissions and plan of action with professor, researched Comodo and got in contact with support2hrs | Discussed with support through email and phone, discussed problem with team as well, reached out to Sectigo 3hrs |  | Created basic WIP UML diagram of new software and organized all extra notes taken regarding licensing issues into note file submitted to github. 2hrs
Lonnie | 7 hours 20 | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30mins |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team (sending appropriate emails and despersing important documents from clients45min | analysis of email exchange to help diagnose the problem. As well as sending multiple emails to our client and her development for further clarification as well as needed documentation 2hrs | consulted team about repsonse to developer's email to try and solve the issue 15mins | consulted demo video given from client to make large list of updated user stories for the web app, as well as used infromtation to start constructing wireframes 3hrs | Finished up Basic wireframes 1hr

## Sprint 2
| HOURS | STATUS | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03
Shahzeb | 20 hours | Active |  |  |  | Started learning Ruby On Rails to get ready for coding. Went through YouTube tutorials for 4 hours. | Meeting with client, performed wireframes demo and got feedback, found out licensing issue should be solved, discussed next steps with group after 1hr | Continues learning Ruby on Rails, looked over legacy code and files that client sent over. 3 hours | [9 empty] | Learned Ruby on Rails, started setting up controllers, views, and installing all necessary software 5 hours | Worked on building new user form on ruby on rails 5 hours | Worked on Ruby on Rails user index page,saving the users to database 2 HOURS
Wilson | 10 hours | Active | Talked to Sectigo support and set up case to provide extra details through as we addressed the problem, was told I would be called back and was never called back regarding my case 2hr | Attempted to call comodossl to discuss the problem, was unable to call so used the live chat feature, got a few answers but needed info from deborah (client). Got in touch with her and waiting for response. Did more research on code signing and next steps. 3hrs | Recieved response from Deborah and she stated she was working with Russel to try some new keys, said we would try to address the issue if these keys did not work. Looked into a bit more support info about the keys she was using. 45min |  | Meeting with client, performed wireframes demo and got feedback, found out licensing issue should be solved, discussed next steps with group after 1hr | Set up Rails environment and attemped to set up github project environment as well. (brushed up on rails and github functions. 1hr 15min | Attempted to set up github environment, having issues getting new rails project to have base info like in 4081. 1hr |  | Fixed issues with Gihub and rails in class, also discussed next steps with team. Fixed minor rails issues and got server running, having issues with home pages but probably minor. 2hrs |  | Attempted to fix the error from tuesday, and posted on help forum in discord for help, did fix some issues with the gemfile and github connections. 1hr 20min | Worked more on rails error, discovered error was within my own system and not an issue with the github or project. Told this to team so they cn continue to work without issue 1hr |  | Fixed the issue within rails after lots of fix attempts, got in contact with team to see about pushing some code and some minor issues pushing to the github. (likely permissions) 2hrs 15min | Worked on organizing the github and setting things up completely, contacted team with questions for meeting tomorrow 30min | Met with team members and finalized fixes on the github and rails environment. Got home page running and github environment working as intended and disucussed presentation and needs for sprint 2 demo day. 2hrs | Added navbar and images to homepage with some working navbar items, ensured code worked before meeting with team and creating new github and pushing code to main branch and finalizing teams changes. 2hrs | Prepped for presentation on demo day, updated all needed files and info for sprint 2 submission 1hr
Lonnie | 8 hours 30 min | Active |  | Organized a plan with team for how we want to structure the project as well as organized a meeting with a client to conduct a user test with our wireframes 1hr | REVAMPED wireframes. more than quadrupled the amount of wireframes by inputting real data as well as interconnectivity between all of them to provide a use a proper user test 3 Hr | Continuted work on revamping wireframes 2hr | Finalized wireframes. Showcased wireframes in a proper user test with our client in a meeting. Discussed the future of the project with client and team 2hr 30 min |  |  |  | overhauled wireframes after user testing and meeting with professor. 3 hrs |  |  | attempted more user testing with personal aquaintances who are going into a similar field but have never used the software. Asked Deborah for people we can user test on. 2 hrs |  |  |  | set up rails enviroment and connected to github. 2hrs