## Sprint 1
| Hours | Status | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19
Shahzeb | 7 hours 25 mins | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30min |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team 45min | Read through and looked at emails that we were sent to better understand the licensing issue taking place. Met with team in class, we sent emails to client to get a demo video of the application, and sent an email to the previous app team to understand what was going on with the licensing 2hours | Looked at demo video that client sent 20 mins | Created User story map, and organized user stories by category, then by priority 2 hours
Wilson | 10 hours 5 mins | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30min |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team 45min | Created basic user stories, discussed submissions and plan of action with professor, researched Comodo and got in contact with support2hrs | Discussed with support through email and phone, discussed problem with team as well, reached out to Sectigo 3hrs |  | Created basic WIP UML diagram of new software and organized all extra notes taken regarding licensing issues into note file submitted to github. 2hrs
Lonnie | 7 hours 20 | Active |  |  | Reached out to team members and set up Discord server 30min | Discussed client meeting with members 30mins |  |  |  | Prepped for client meeting, made questions, worked on contract and set up team roles 1hr 20min | Meeting with client, got first task, began work on it after discussing with team (sending appropriate emails and despersing important documents from clients45min | analysis of email exchange to help diagnose the problem. As well as sending multiple emails to our client and her development for further clarification as well as needed documentation 2hrs | consulted team about repsonse to developer's email to try and solve the issue 15mins | consulted demo video given from client to make large list of updated user stories for the web app, as well as used infromtation to start constructing wireframes 2hrs